## Sheet1
Stakeholder Group | Awareness | Desire | Knowledge | Ability | Reinforcement | Key Risk | Mitigation Action | Delivery Implication
Representatives | High. They know the current system is inefficient and stressful. | Medium. They want relief from manual work but fear fragile automation and unclear exception handling. | Medium. They understand the workflow but not how the new system will behave in edge cases. | Medium. They can adopt the new system if it is simple, predictable, and reduces manual reconciliation. | Medium. Reinforcement comes from seeing fewer missed follow-ups and less spreadsheet work. | They bypass the new system if it feels incomplete, slow, or unclear, reverting back to familiar spreadsheets and manual tracking. | Co-design and test early prototypes with representatives to ensure flows are simple, predictable, and cover real-world exceptions. | Should this become a backlog item or reporting need?
Team leaders and managers | High. They see the operational pain daily. | Medium-High. They want improvement, but only if visibility and exception handling improve. | Medium. They understand the workflow but need clarity on how automation supports oversight. | Medium. They can adopt the new system if reporting is reliable, exception and escalation paths are clearly defined, and the workflow is fully observable. It depends on whether the system consistently works and saves time. | Medium-High. Reinforcement comes from improved observability and fewer reconciliation tasks. | They lose confidence in the new system if they cannot see work progressing in real time. | Deliver operational evidence and insights in Phase 1 that provide live visibility of workload, status changes, and escalation pathways. | Should manager visibility appear in Phase 1?
Operations leadership | High. They understand the scale of inefficiency and revenue leakage. | Medium. They want improvement but need confidence that Phase 1 delivers measurable uplift. | Low-Medium. They won't be involved in planning and will rely on clear, defensible briefings. | Medium. They can adopt the new system if the plan is concrete and risk-controlled. | Low-Medium. Reinforcement comes from early wins and clear KPIs. | They hesitate to approve Phase 1 if the logic is unclear or not tied directly to measurable operational uplift. | Define clear KPIs (e.g., reduced duplicate contact, fewer missed follow-ups) and link each Phase 1 feature to a specific metric. | What evidence will they want after launch?
Finance | High. They understand the financial impact of inefficiency. | Medium. They support the problem but need a defensible plan before approving funding. | Low-Medium. They won't be involved in planning and need clarity on scope, assumptions, and sensitivity. | Medium. They can approve funding if the plan is concrete and risk-controlled. | Low. Reinforcement comes from early financial indicators and evidence-based performance insights. | Funding does not get approved if Phase 1 scope, assumptions, and trade-offs are not defensible or transparent. | Provide a clear, concise, evidence-based scope brief with explicit assumptions, sensitivity ranges, and a clear explanation of how Phase 1 reduced operational waste. | What keeps the value case credible?
Product and delivery | High. They know Phase 1 is approaching and feel the delivery pressure. | High. They want clarity, buildability, and scope discipline. | Medium-High. They understand delivery but need precise requirements and dependencies. | Medium-High. They can deliver Phase 1 if the requirements are precise, testable, and traceable to discovery evidence. | High. Reinforcement comes from scope, reduced rework, and a prototype that matches the backlog. | Delivery slows or stops if requirements are ambiguous, untestable, or expand beyond the agreed Phase 1 scope. | Produce precise, testable user stories, tied directly to discovery evidence, and clearly define Phase 1 scope early to prevent scope creep. | What scope or dependency risk must be controlled?